## 2022 Budget
2020
Expense | [16 empty] | Notes
| 2022 Budget | 2022 Actual | 2021 Budget | 2021 Actual | 2020 Budget | 2020 Actual | 2019 Budget | 2019 Actual | 2018 Budget | 2018 Actual | 2017 budget | 2017 actual | 2016 Budget | 2016 Actual | 2015 Budget | 2015 Actual |  | Justification
Admin | 2500 |  | 2500 | 2350 | 3000 | 3050 | 3000 | 2660 | 3000 | 3525 | 3000 | 3335 | 2500 | 3980 | 2000 | 4111.25 |  | same as last year
Boundary UWR | 500 |  | 500 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 4220 | 4220 | 2355.75 | 6299.33 | 1000 | 3780 |  | same as last year
WK UWR | 500 |  | 500 | 0 | 0 | 500 | 3000 | 0 | 3000 | 2920 | 1780 | 0 | 0 | 0 | 0 | 0 |  | same as last year
Biodiversity Report | 500 |  | 500 | 0 | 3000 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | same as last year
Update resultants, depletion | 5000 |  | 5000 | 5200 | 8500 | 7400 | 6500 | 4740 | 7500 | 7850 | 10000 | 8000 | 2000 | 12520 | 13000 | 13556.45 |  | same as last year
Website maintenance | 2000 |  | 2000 | 500 | 2000 | 1350 | 2000 | 3360 | 2750 | 2000 | 1850 | 2920 | 1850 | 1860 | 1000 | 1106.25 |  | same as last year
Subscriber support | 1500 |  | 1500 | 700 | 1500 | 1200 | 2500 | 1040 | 2500 | 2320 | 1500 | 3300 | 1000 | 1320 | 0 | 0 |  | same as last year
Quality Assurance | 3000 |  | 3000 | 3400 | 6031.19 | 4550 | 2000 | 5720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2642.5 |  | same as last year
Boundary Moose UWR | 1000 |  | 2500 | 1900 | [13 empty] | Total project budget estimate $2500, spent $1900 in 2021
Future condition | 3000 |  | 1200 | 100 | [13 empty] | Project not started yet, budgeted for $1200
Unallocated | 3300.95 |  | 4507 | 0 | 0 | 0 | 6913.1 |  | 9640.65 |  | 0 | 0
Total Expenses | 22800.95 |  | 20007 | 14150 | 24031.19 | 21050 | 25913.1 | 17520 | 28390.65 | 18615 | 22350 | 21775 | 9705.75 | 25979.33 | 17000 | 25196.45
Revenue
Assuming No Change from 2021 AAC Allocations
|  | 2022 at $.005 |  | 2021 at $.005 |  | 2020 at $.005 |  | 2019 at $.005 |  | 2018 at $0.01 | 2018 Received + Committed | 2017 at $0.015
FLNRO |  | 2500 |  | 2500 |  | 2500 |  | 2500 |  | 5000 | 4500 | 5000
BCTS |  | 3534.37 |  | 3534.37 |  | 3534.37 |  | 3590.52 |  | 7181.04 | 7181.04 | 10771.56
Kalesnikoff |  | 500 |  | 500 |  | 500 |  | 500 |  | 899.5 | 899.5 | 1349.25
Interfor |  | 5550.61 |  | 5688.61 |  | 5688.61 |  | 5688.61 |  | 11377.21 | 11377.21 | 17065.82
NACFOR |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 | 500 | 750
Atco |  | 858.97 |  | 858.97 |  | 858.97 |  | 858.97 |  | 1717.94 | 1717.94 | 2576.91
SIFCo |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 | 500 | 750
KDCFS |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 | 500
Vaagen - West Boundary CF |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 | 500
Vaagen - Osoyoos Indian Band |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 | 500
Tolko |  | 500 |  | 500
Stella-Jones |  | 500 |  | 500
Cooper Creek Cedar |  | 500 |  | 500
Total Revenue |  | 16943.95 |  | 17081.95 |  | 15581.95 |  | 15638.1 |  | 28675.69 | 28175.69 | 38263.54
Surplus/Deficit Carry over
Debt / Credit |  | 5857 |  | 2925.05 |  | 8393.1 |  | 10275 |  | 214.96 |  | -15913.54
Total Balance |  | 22800.95 |  | 20007 |  | 23975.05 |  | 25913.1 |  | 28890.65 |  | 22350

## Jan 2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 350 | 2500 | 2150 | 2150 | 86% |  |  | Prep budget 2 x meetings, update website
Boundary UWR (Ian D) |  | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). |  | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) |  | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) |  | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) |  | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) |  | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance |  | 0 | 3000 | 3000 | 3000 | 100%
Boundary Moose UWR |  | 0 | 1000 | 1000 | 1000 | 100%
Future condition |  | 0 | 3000 | 3000 | 3000 | 100%
Unallocated |  | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 350 | 22800.95 | 22450.95 | 22450.95 | 98.46%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Feb 2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 750 | 2500 | 1750 | 1750 | 70% |  |  | Adjusting AAC amounts, prepping subscription agreements
Boundary UWR (Ian D) |  |  | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). |  |  | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) |  |  | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) |  |  | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) |  |  | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) |  |  | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance |  |  | 0 | 3000 | 3000 | 3000 | 100%
Boundary Moose UWR |  |  | 0 | 1000 | 1000 | 1000 | 100%
Future condition |  |  | 0 | 3000 | 3000 | 3000 | 100%
Unallocated |  |  | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 750 | 22800.95 | 22050.95 | 22050.95 | 96.71%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Mar 2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 850 | 2500 | 1650 | 1650 | 66% |  |  | Prepare Invoices
Boundary UWR (Ian D) |  |  |  | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). |  |  |  | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) |  |  |  | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) |  |  |  | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) |  |  |  | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) |  |  |  | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance |  |  |  | 0 | 3000 | 3000 | 3000 | 100%
Boundary Moose UWR |  |  |  | 0 | 1000 | 1000 | 1000 | 100%
Future condition |  |  |  | 0 | 3000 | 3000 | 3000 | 100%
Unallocated |  |  |  | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 850 | 22800.95 | 21950.95 | 21950.95 | 96.27%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Apr 2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 1100 | 2500 | 1400 | 1400 | 56% |  |  | Meeting, new subscription agreement, Budget Reports
Boundary UWR (Ian D) |  |  |  |  | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). |  |  |  |  | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) |  |  |  |  | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) |  |  |  |  | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) |  |  |  |  | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) |  |  |  |  | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance |  |  |  |  | 0 | 3000 | 3000 | 3000 | 100%
Boundary Moose UWR |  |  |  |  | 0 | 1000 | 1000 | 1000 | 100%
Future condition |  |  |  | 25 | 25 | 3000 | 2975 | 2975 | 99.17% |  |  | Formulation of requirements of data needed from subscribers
Unallocated |  |  |  |  | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 | 1125 | 22800.95 | 21675.95 | 21675.95 | 95.07%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## May 2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | May 1 -May 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 50 | 1150 | 2500 | 1350 | 1350 | 54% |  |  | Email and call with Ian W on wording in new subscription agreement
Boundary UWR (Ian D) | [5 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [5 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [5 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) | [5 empty] | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | [5 empty] | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance | [5 empty] | 0 | 3000 | 3000 | 3000 | 100%
Boundary Moose UWR |  |  |  |  | 500 | 500 | 1000 | 500 | 500 | 50% |  |  | QA of Moose data by comparison with IPAC report provicded by Randy
Future condition |  |  |  | 25 | 25 | 50 | 3000 | 2950 | 2950 | 98.33% |  |  | Data from BCTS
Unallocated | [5 empty] | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 |  | 1700 | 22800.95 | 21100.95 | 21100.95 | 92.54%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Jun 2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | May 1 -May 31 | Jun 1 Jun 30 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 50 | 200 | 1350 | 2500 | 1150 | 1150 | 46% |  |  | 2 meetings, prep reports, update website
Boundary UWR (Ian D) | [6 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [6 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [6 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 800 | 800 | 5000 | 4200 | 4200 | 84% |  |  | 2022 build
Website maintenance (Ian, Ian D.) | [6 empty] | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | [6 empty] | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance | [5 empty] | 500 | 500 | 3000 | 2500 | 2500 | 83.33% |  |  | 2022 QA + fire analysy
Boundary Moose UWR |  |  |  |  | 500 | 400 | 900 | 1000 | 100 | 100 | 10% |  |  | meeting, data analysis qa
Future condition |  |  |  | 25 | 25 |  | 50 | 3000 | 2950 | 2950 | 98.33%
Unallocated | [6 empty] | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 | 575 | 1900 | 3600 | 22800.95 | 19200.95 | 19200.95 | 84.21%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Jul 2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | May 1 -May 31 | Jun 1 Jun 30 | Jul 1 - Jul 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 50 | 200 |  | 1350 | 2500 | 1150 | 1150 | 46%
Boundary UWR (Ian D) | [7 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [7 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [7 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 800 |  | 800 | 5000 | 4200 | 4200 | 84%
Website maintenance (Ian, Ian D.) | [7 empty] | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | [7 empty] | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance | [5 empty] | 500 |  | 500 | 3000 | 2500 | 2500 | 83.33%
Boundary Moose UWR |  |  |  |  | 500 | 400 |  | 900 | 1000 | 100 | 100 | 10%
Future condition |  |  |  | 25 | 25 |  |  | 50 | 3000 | 2950 | 2950 | 98.33%
Unallocated | [7 empty] | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 | 575 | 1900 | 0 | 3600 | 22800.95 | 19200.95 | 19200.95 | 84.21%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Aug 2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | May 1 -May 31 | Jun 1 Jun 30 | Jul 1 - Jul 31 | Aug 1 Aug 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 50 | 200 |  |  | 1350 | 2500 | 1150 | 1150 | 46%
Boundary UWR (Ian D) | [8 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [8 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [8 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 800 |  |  | 800 | 5000 | 4200 | 4200 | 84%
Website maintenance (Ian, Ian D.) | [8 empty] | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | [8 empty] | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance | [5 empty] | 500 |  |  | 500 | 3000 | 2500 | 2500 | 83.33%
Boundary Moose UWR |  |  |  |  | 500 | 400 |  |  | 900 | 1000 | 100 | 100 | 10%
Future condition |  |  |  | 25 | 25 |  |  |  | 50 | 3000 | 2950 | 2950 | 98.33%
Unallocated | [8 empty] | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 | 575 | 1900 | 0 | 0 | 3600 | 22800.95 | 19200.95 | 19200.95 | 84.21%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Sep_2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | May 1 -May 31 | Jun 1 Jun 30 | Jul 1 - Jul 31 | Aug 1 Aug 31 | Sep1 Sep 30 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 50 | 200 |  |  | 100 | 1450 | 2500 | 1050 | 1050 | 42% |  | meeting
Boundary UWR (Ian D) | [9 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [9 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [9 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 800 |  |  |  | 800 | 5000 | 4200 | 4200 | 84%
Website maintenance (Ian, Ian D.) | [9 empty] | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | [9 empty] | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance | [5 empty] | 500 |  |  | 200 | 700 | 3000 | 2300 | 2300 | 76.67% |  | Research and correpondence with Deb Mcillop about the inventory code I polygons
Boundary Moose UWR |  |  |  |  | 500 | 400 |  |  |  | 900 | 1000 | 100 | 100 | 10%
Future condition |  |  |  | 25 | 25 |  |  |  |  | 50 | 3000 | 2950 | 2950 | 98.33%
Unallocated | [9 empty] | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 | 575 | 1900 | 0 | 0 | 300 | 3900 | 22800.95 | 18900.95 | 18900.95 | 82.9%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Oct_2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | May 1 -May 31 | Jun 1 Jun 30 | Jul 1 - Jul 31 | Aug 1 Aug 31 | Sep1 Sep 30 | Oct 1 - Oct 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 50 | 200 |  |  | 100 |  | 1450 | 2500 | 1050 | 1050 | 42% |  | meeting
Boundary UWR (Ian D) | [10 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [10 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [10 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 800 |  |  |  |  | 800 | 5000 | 4200 | 4200 | 84%
Website maintenance (Ian, Ian D.) | [10 empty] | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | [10 empty] | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance | [5 empty] | 500 |  |  | 200 | 500 | 1200 | 3000 | 1800 | 1800 | 60% |  | Research and correpondence with Deb Mcillop about the inventory code I polygons
Boundary Moose UWR |  |  |  |  | 500 | 400 |  |  |  |  | 900 | 1000 | 100 | 100 | 10%
Future condition |  |  |  | 25 | 25 | [5 empty] | 50 | 3000 | 2950 | 2950 | 98.33%
Unallocated | [10 empty] | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 | 575 | 1900 | 0 | 0 | 300 | 500 | 4400 | 22800.95 | 18400.95 | 18400.95 | 80.7%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Nov_2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | May 1 -May 31 | Jun 1 Jun 30 | Jul 1 - Jul 31 | Aug 1 Aug 31 | Sep1 Sep 30 | Oct 1 - Oct 31 | Nov 1 - Nov 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 50 | 200 |  |  | 100 |  | 200 | 1650 | 2500 | 850 | 850 | 34% |  | meeting, financial reports, billing for Gfox
Boundary UWR (Ian D) | [11 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [11 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [11 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 800 |  |  |  |  | 1400 | 2200 | 5000 | 2800 | 2800 | 56% |  | Updating and testing logic with burns, new ownership rules, new net down logic for Inventory std I
Website maintenance (Ian, Ian D.) | [11 empty] | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | [11 empty] | 0 | 1500 | 1500 | 1500 | 100%
Quality Assurance | [5 empty] | 500 |  |  | 200 | 500 |  | 1200 | 3000 | 1800 | 1800 | 60%
Boundary Moose UWR |  |  |  |  | 500 | 400 |  |  |  |  | 200 | 1100 | 1000 | -100 | -100 | -10% |  | 2021 Moose tables go live on website
Future condition |  |  |  | 25 | 25 | [6 empty] | 50 | 3000 | 2950 | 2950 | 98.33%
Unallocated | [11 empty] | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 | 575 | 1900 | 0 | 0 | 300 | 500 | 1800 | 6200 | 22800.95 | 16600.95 | 16600.95 | 72.81%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Dec_2022
#VALUE!
Income
2021 Credit Carry Over | 5857
2022 Contribution | 16943.95
Total Available Funds | 22800.95
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30 | May 1 -May 31 | Jun 1 Jun 30 | Jul 1 - Jul 31 | Aug 1 Aug 31 | Sep1 Sep 30 | Oct 1 - Oct 31 | Nov 1 - Nov 30 | Dec - Dec 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 350 | 400 | 100 | 250 | 50 | 200 |  |  | 100 |  | 200 | 200 | 1850 | 2500 | 650 | 650 | 26% |  | meeting, financial reports, web updates
Boundary UWR (Ian D) | [12 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [12 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [12 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 800 |  |  |  |  | 1400 | 800 | 3000 | 5000 | 2000 | 2000 | 40% |  | Rebuild tables as result of QA investigation, rebuild again as a result of confusion over woodlots
Website maintenance (Ian, Ian D.) | [12 empty] | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | [11 empty] | 100 | 100 | 1500 | 1400 | 1400 | 93.33% |  | Respond to Email from folks at CABIN re new tables
Quality Assurance | [5 empty] | 500 |  |  | 200 | 500 |  | 1550 | 2750 | 3000 | 250 | 250 | 8.333% |  | QA of new tables, bug fixes and re-evaluate
Boundary Moose UWR |  |  |  |  | 500 | 400 |  |  |  |  | 200 |  | 1100 | 1000 | -100 | -100 | -10%
Future condition |  |  |  | 25 | 25 | [7 empty] | 50 | 3000 | 2950 | 2950 | 98.33%
Unallocated | [12 empty] | 0 | 3300.95 | 3300.95 | 3300.95 | 100%
Total Expenses | 350 | 400 | 100 | 275 | 575 | 1900 | 0 | 0 | 300 | 500 | 1800 | 2650 | 8850 | 22800.95 | 13950.95 | 13950.95 | 61.19%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.