## 2019DraftBudget
| 2019 Budget | 2018 Budget | 2018 Actual | 2017 budget (after UWR change) | 2017 actual |  | 2016 Budget | 2016 Actual | 2015 Budget | 2015 Actual
Debt / Credit | -10275 | -214.955 | -214.955 | 16273.58 | 16273.58 |  | 16404.55 | 16404.55 | 10000 | 10000
Admin | 3000 | 3000 | 3525 | 3000 | 3335 |  | 2500 | 3980 | 2000 | 4111.25
Boundary UWR | 0 | 0 | 0 | 4220 | 4220 |  | 2355.75 | 6299.33 | 1000 | 3780
WK UWR | 3000 | 3000 | 2920 | 1780 | 0 |  | 0 | 0 | 0 | 0
Update resultants, depletion | 6500 | 7500 | 7850 | 10000 | 8000 |  | 2000 | 12520 | 13000 | 13556.45
Website maintenance | 2000 | 2750 | 2000 | 1850 | 2920 |  | 1850 | 1860 | 1000 | 1106.25
Subscriber support | 2500 | 2500 | 2320 | 1500 | 3300 |  | 1000 | 1320 | 0 | 0
Quality Assurance | 2000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2642.5
Unallocated | 5612.85 | 9640.645 | 9640.645 | 0 | 0 |  | 26110.3 | 42383.88 | 27000 | 35196.45
Total Expenses | 14337.85 | 28175.69 | 28040.69 | 38623.58 | 38048.58
Revenue
Assuming No Change from 2018 AAC Allocations
| 2019 at $0.01 | 2019 at $.0075 | 2019 at $.005 | 2018 at $0.01 | 2018 Received | 2017 at $0.015
FLNRO | 5000 | 3750 | 2500 | 5000 | 4500 | 5000
BCTS | 7181.04 | 5385.78 | 3590.52 | 7181.04 | 7181.04 | 10771.56
Kalesnikoff | 899.5 | 674.625 | 449.75 | 899.5 | 899.5 | 1349.25
Interfor | 11377.21 | 8532.9075 | 5688.605 | 11377.21 | 11377.21 | 17065.815
NACFOR | 500 | 375 | 250 | 500 | 500 | 750
Atco | 1717.94 | 1288.455 | 858.97 | 1717.94 | 1717.94 | 2576.91
SIFCo | 500 | 375 | 250 | 500 | 500 | 750
KDCFS | 500 | 375 | 250 | 500 | 500 | 38263.535
Vaagen - West Boundary CF | 500 | 375 | 250 | 500 | 500
Vaagen - Osoyoos Indian Band | 500 | 375 | 250 | 28175.69 | 27675.69
Total Revenue | 28675.69 | 21506.7675 | 14337.845

## 2020Budget
2020
Expense | [12 empty] | Notes
| 2020 Budget | 2020 Actual | 2019 Budget | 2019 Actual | 2018 Budget | 2018 Actual | 2017 budget | 2017 actual | 2016 Budget | 2016 Actual | 2015 Budget | 2015 Actual
Admin | 3000 |  | 3000 | 2660 | 3000 | 3525 | 3000 | 3335 | 2500 | 3980 | 2000 | 4111.25 | same as 2019
Boundary UWR | 0 |  | 0 | 0 | 0 | 0 | 4220 | 4220 | 2355.75 | 6299.33 | 1000 | 3780 | No projected new work
WK UWR | 0 |  | 3000 | 0 | 3000 | 2920 | 1780 | 0 | 0 | 0 | 0 | 0 | No projected new work
Biodiversity Report | 3000 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | New project
Update resultants, depletion | 8500 |  | 6500 | 4740 | 7500 | 7850 | 10000 | 8000 | 2000 | 12520 | 13000 | 13556.45 | 2019 still needs finishind so extra $1000 added
Website maintenance | 2000 |  | 2000 | 3360 | 2750 | 2000 | 1850 | 2920 | 1850 | 1860 | 1000 | 1106.25 | This was over budget in 2019 so allocation increased by $1000 - maybe not necessary to increase
Subscriber support | 1500 |  | 2500 | 1040 | 2500 | 2320 | 1500 | 3300 | 1000 | 1320 | 0 | 0 | This was under budget in 2019 so allocation cut by $1000
Quality Assurance | 6031.19 |  | 2000 | 5720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2642.5 | This was way over budget in 2019 so allocation increased with all unallocated funds
Unallocated | 0 |  | 6913.1 |  | 9640.645 |  | 0 | 0
Total Expenses | 24031.19 |  | 25913.1 | 17520 | 28390.645 | 18615 | 22350 | 21775 | 9705.75 | 25979.33 | 17000 | 25196.45
Revenue
Assuming No Change from 2018 AAC Allocations
| 2020 at $.005 |  | 2019 at $.005 |  | 2018 at $0.01 | 2018 Received + Committed | 2017 at $0.015
FLNRO | 2500 |  | 2500 |  | 5000 | 4500 | 5000
BCTS | 3590.52 |  | 3590.52 |  | 7181.04 | 7181.04 | 10771.56
Kalesnikoff | 500 |  | 500 |  | 899.5 | 899.5 | 1349.25
Interfor | 5688.605 |  | 5688.605 |  | 11377.21 | 11377.21 | 17065.815
NACFOR | 500 |  | 500 |  | 500 | 500 | 750
Atco | 858.97 |  | 858.97 |  | 1717.94 | 1717.94 | 2576.91
SIFCo | 500 |  | 500 |  | 500 | 500 | 750
KDCFS | 500 |  | 500 |  | 500 | 500
Vaagen - West Boundary CF | 500 |  | 500 |  | 500 | 500
Vaagen - Osoyoos Indian Band | 500 |  | 500 |  | 500 | 500
Total Revenue | 15638.095 |  | 15638.095 |  | 28675.69 | 28175.69 | 38263.535
Surplus/Deficit Carry over
Debt / Credit | 8393.1 |  | 10275 |  | 214.955 |  | -15913.535
Total Balance | 24031.195 |  | 25913.095 |  | 28890.645 |  | 22350

## Jan 2020
HLPORS Financial Report Jan 2020
Income
2019 Credit Carry Over | 8393.1
2019 Contribution | 15638.095
Total Available Funds | 24031.195
Expenses
| Jan 1 - Jan 23 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 1100 | 1100 | 3000 | 1900 | 1900 | 63.33% | 8.333% |  | budget subcomitee and full meeting, preparing reports and budget, making changes to reporting format
Boundary UWR (Ian D) |  | 0 | 0 | 0 | 0 | 0%
WK UWR (Ian D). | 100 | 100 | 0 | -100 | -100 | #DIV/0! |  |  | Updated the report on the website to the test version that had the LU removed
Biodiversity Report (Ian D) | 2100 | 2100 | 3000 | 900 | 900 | 30% | 90% |  | Created working version of report, and went through one round of debugging
Update resultants, depletion (Ian D.) | 600 | 600 | 8500 | 7900 | 7900 | 92.94% |  |  | Trying different buffer on road layer, and incorporating layer for Gas and Electricity transmission lines
Website maintenance (Ian, Ian D.) |  | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | 100 | 100 | 1500 | 1400 | 1400 | 93.33% | 8.333% |  | Responded to a request from Loreen as to how the connectivity was calculated
Quality Assurance |  | 0 | 6031.19 | 6031.19 | 6031.19 | 100%
Unallocated |  | 0 | 0 | 0 | 0 | #DIV/0!
Total Expenses | 4000 | 4000 | 24031.19 | 20031.19 | 20031.19 | 83.35%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Feb 2020
HLPORS Financial Report Feb 2020
Income
2019 Credit Carry Over | 8393.1
2019 Contribution | 15638.095
Total Available Funds | 24031.195
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 29 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 1100 | 100 | 1200 | 3000 | 1800 | 1800 | 60% | 16.67% |  | Preparing Jan financial statement
Boundary UWR (Ian D) |  |  | 0 | 0 | 0 | 0 | 0%
WK UWR (Ian D). | 100 |  | 100 | 0 | -100 | -100 | #DIV/0!
Biodiversity Report (Ian D) | 2100 | 100 | 2200 | 3000 | 800 | 800 | 26.67% | 90% |  | Adding additional explanatory text to the from
Update resultants, depletion (Ian D.) | 600 | 100 | 700 | 8500 | 7800 | 7800 | 91.76% |  |  | Upload road layers and buffer polygons to ftp site as requested by loreen
Website maintenance (Ian, Ian D.) |  |  | 0 | 2000 | 2000 | 2000 | 100%
Subscriber support (Ian, Ian D.) | 100 |  | 100 | 1500 | 1400 | 1400 | 93.33% | 16.67%
Quality Assurance |  |  | 0 | 6031.19 | 6031.19 | 6031.19 | 100%
Unallocated |  |  | 0 | 0 | 0 | 0
Total Expenses | 4000 | 300 | 4300 | 24031.19 | 19731.19 | 19731.19 | 82.11%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Mar 2020
HLPORS Financial Report Mar 2020
Income
2019 Credit Carry Over | 8393.1
2019 Contribution | 15638.095
Total Available Funds | 24031.195
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 29 | Mar1-31st | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 1100 | 100 | 250 | 1450 | 3000 | 1550 | 1550 | 51.67% | 16.67% |  | Preparing feb financial statement and March Meeting
Boundary UWR (Ian D) |  |  |  | 0 | 0 | 0 | 0 | 0%
WK UWR (Ian D). | 100 |  |  | 100 | 0 | -100 | -100 | #DIV/0!
Biodiversity Report (Ian D) | 2100 | 100 | 200 | 2400 | 3000 | 600 | 600 | 20% | 95% |  | Last few modifications to table, and republish reports
Update resultants, depletion (Ian D.) | 600 | 100 | 700 | 1400 | 8500 | 7100 | 7100 | 83.53% |  |  | Work on finding suitable road layer - tried new buffers on 2017 CE layer from Ian W, Calculating area and length totals for each road class/forest district as requested by Loreen. Spatial comparison of 2015/2017 data
Website maintenance (Ian, Ian D.) |  |  | 100 | 100 | 2000 | 1900 | 1900 | 95% |  |  | Adding meeting notes to site
Subscriber support (Ian, Ian D.) | 100 |  |  | 100 | 1500 | 1400 | 1400 | 93.33% | 16.67%
Quality Assurance |  |  |  | 0 | 6031.19 | 6031.19 | 6031.19 | 100%
Unallocated |  |  |  | 0 | 0 | 0 | 0
Total Expenses | 4000 | 300 | 1250 | 5550 | 24031.19 | 18481.19 | 18481.19 | 76.91%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Apr 2020
HLPORS Financial Report Apr 2020
Income
2019 Credit Carry Over | 8393.1
2019 Contribution | 15638.095
Total Available Funds | 24031.195
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 29 | Mar1-31st | Apr1 - 30 | YTD | Annual Allocation | Budget Remaining | % Budget Remaining | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 1100 | 100 | 250 | 150 | 1600 | 3000 | 1400 | 46.67% | 33.33% |  | March Financial statement
Boundary UWR (Ian D) |  |  |  | 100 | 100 | 0 | -100 | #DIV/0! |  |  | Answering question about uwr rank
WK UWR (Ian D). | 100 |  |  |  | 100 | 0 | -100 | #DIV/0!
Biodiversity Report (Ian D) | 2100 | 100 | 200 | 300 | 2700 | 3000 | 300 | 10% | 100% |  | Publish new report to website, some changes required to database and web pages to accommodate new report (ie remove buttons for standard or seral reports, remove modeeling runs with ogmas off)
Update resultants, depletion (Ian D.) | 600 | 100 | 700 | 2800 | 4200 | 8500 | 4300 | 50.59% | 100% for 2019 |  | Create agreed upon roads layer based on 2015 roads, pipelines, transmission lines and Raillines. Build 2019 resultant with this data, QA, fix error in roads self overlap, rebuild resultant. Fix problems for BEO values and Boundary road density calculations. More conversations about road data with Loreen, Randy and Kathleen. Provide Loreen with original 2015 road data and buffer tables. Fix boundary road denisty calculation. Publish all data, reports and QA to website
Website maintenance (Ian, Ian D.) |  |  | 100 | 550 | 650 | 2000 | 1350 | 67.5% |  |  | Added source data header to Boundary uwr report. Made all source data not in dataBC available from selkirk ftp site via help pages. Restricted available resultants to upload cutblocks to only stock resultants. Rebooted a crashed server. Modified footer on Boundary uwr report
Subscriber support (Ian, Ian D.) | 100 |  |  | 100 | 200 | 1500 | 1300 | 86.67% | 33.33% |  | Support for Gavin Fox on spatial upload tool and a reboot to the jasper report server
Quality Assurance |  |  |  | 2450 | 2450 | 6031.19 | 3581.19 | 59.38% | 100% for 2019 |  | producing QA tables for 2019 resultant. Reviewing issues in Loreens QA word document. QA subcomitee meeting. QA data for subproject ananlysis of TFL3 roads using different buffers on CE2017 roads layer
Unallocated |  |  |  |  | 0 | 0 | 0 | #DIV/0!
Total Expenses | 4000 | 300 | 1250 | 6450 | 12000 | 24031.19 | 12031.19 | 50.06%
No project/line item can have a negative Budget remainingunless the steering committee has previously approved the over expenditure.
If % budget remaining for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## May 2020
HLPORS Financial Report May 2020
Income
2019 Credit Carry Over | 8393.1
2019 Contribution | 15638.095
Total Available Funds | 24031.195
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 29 | Mar1-31st | Apr1 - 30 | May 1-31 | YTD | Annual Allocation | Budget Remaining | % Budget Remaining | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 1100 | 100 | 250 | 150 | 350 | 1950 | 3000 | 1050 | 35% | 41.67% |  | April Statement and setup zoom webinar, may meeting
Boundary UWR (Ian D) |  |  |  | 100 |  | 100 | 0 | -100 | #DIV/0!
WK UWR (Ian D). | 100 |  |  |  |  | 100 | 0 | -100 | #DIV/0!
Biodiversity Report (Ian D) | 2100 | 100 | 200 | 300 |  | 2700 | 3000 | 300 | 10% | 100%
Update resultants, depletion (Ian D.) | 600 | 100 | 700 | 2800 | 750 | 4950 | 8500 | 3550 | 41.76% | 100% for 2019, 20% for 2020 |  | Completed 2020 Depletion resultant. Planning Coop student work for road corrections to CE2017 layer
Website maintenance (Ian, Ian D.) |  |  | 100 | 550 | 200 | 850 | 2000 | 1150 | 57.5% |  |  | Changes request by Loreen regarding wording and removing old documents. Clean up of old files from database
Subscriber support (Ian, Ian D.) | 100 |  |  | 100 | 600 | 800 | 1500 | 700 | 46.67% | 41.67% |  | Webinar pre meeting, prep and webinar
Quality Assurance |  |  |  | 2450 | 400 | 2850 | 6031.19 | 3181.19 | 52.75% | 100% for 2019 |  | RE Run Kathleen's roads for whole of TFL3. Researched question for Loreen as to why boundary road density did not appear to add up
Unallocated | [5 empty] | 0 | 0 | 0 | #DIV/0!
Total Expenses | 4000 | 300 | 1250 | 6450 | 2300 | 14300 | 24031.19 | 9731.19 | 40.49%
No project/line item can have a negative Budget remainingunless the steering committee has previously approved the over expenditure.
If % budget remaining for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## June 2020
HLPORS Financial Report Jun 2020
Income
2019 Credit Carry Over | 8393.1
2019 Contribution | 15638.095
Total Available Funds | 24031.195
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 29 | Mar1-31st | Apr1 - 30 | May 1-31 | June1-30 | YTD | Annual Allocation | Budget Remaining | % Budget Remaining | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 1100 | 100 | 250 | 150 | 350 | 300 | 2250 | 3000 | 750 | 25% | 50% | Preparing budget and June subscriber meeting
Boundary UWR (Ian D) |  |  |  | 100 |  |  | 100 | 0 | -100 | #DIV/0!
WK UWR (Ian D). | 100 | [5 empty] | 100 | 0 | -100 | #DIV/0!
Biodiversity Report (Ian D) | 2100 | 100 | 200 | 300 |  |  | 2700 | 3000 | 300 | 10% | 100%
Update resultants, depletion (Ian D.) | 600 | 100 | 700 | 2800 | 750 | 200 | 5150 | 8500 | 3350 | 39.41% | 100% for 2019, 20% for 2020 | Call with Kathleen Mcguiness to get demostration on her methodology for classing roads by hand, then follow up call with Ian Wiles about using Kathleen's method with a student
Website maintenance (Ian, Ian D.) |  |  | 100 | 550 | 200 | 200 | 1050 | 2000 | 950 | 47.5% |  | Video editing and publishing of videos to Youtube for the 2020 webinar
Subscriber support (Ian, Ian D.) | 100 |  |  | 100 | 600 | 100 | 900 | 1500 | 600 | 40% | 50% | Answering query for KDFCS caused by imap BC labelling an MU differently to the data catalog layer
Quality Assurance |  |  |  | 2450 | 400 | 400 | 3250 | 6031.19 | 2781.19 | 46.11% | 100% for 2019 | Bug fix, checking and new reports for when Randy pointed out the targets were incorrect on the suite
Unallocated | [6 empty] | 0 | 0 | 0 | #DIV/0!
Total Expenses | 4000 | 300 | 1250 | 6450 | 2300 | 1200 | 15500 | 24031.19 | 8531.19 | 35.5%
No project/line item can have a negative Budget remainingunless the steering committee has previously approved the over expenditure.
If % budget remaining for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Jul 2020
HLPORS Financial Report Jul 2020
Income
2019 Credit Carry Over | 8393.1
2019 Contribution | 15638.095
Total Available Funds | 24031.195
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 29 | Mar1-31st | Apr1 - 30 | May 1-31 | June1-30 | Jul 1 -31 | YTD | Annual Allocation | Budget Remaining | % Budget Remaining | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 1100 | 100 | 250 | 150 | 350 | 300 | 150 | 2400 | 3000 | 600 | 20% | 58.33% | June budget report and preparing 2020 Subscriber Agreements
Boundary UWR (Ian D) |  |  |  | 100 |  |  |  | 100 | 0 | -100 | #DIV/0!
WK UWR (Ian D). | 100 | [6 empty] | 100 | 0 | -100 | #DIV/0!
Biodiversity Report (Ian D) | 2100 | 100 | 200 | 300 |  |  |  | 2700 | 3000 | 300 | 10% | 100%
Update resultants, depletion (Ian D.) | 600 | 100 | 700 | 2800 | 750 | 200 |  | 5150 | 8500 | 3350 | 39.41% | 100% for 2019, 20% for 2020
Website maintenance (Ian, Ian D.) |  |  | 100 | 550 | 200 | 200 |  | 1050 | 2000 | 950 | 47.5%
Subscriber support (Ian, Ian D.) | 100 |  |  | 100 | 600 | 100 |  | 900 | 1500 | 600 | 40% | 58.33%
Quality Assurance |  |  |  | 2450 | 400 | 400 | 200 | 3450 | 6031.19 | 2581.19 | 42.8% | 100% for 2019 | Investigating problem of Boundary Ungulates not changing when applying an update - Ron never wrote code to do this
Unallocated | [7 empty] | 0 | 0 | 0 | #DIV/0!
Total Expenses | 4000 | 300 | 1250 | 6450 | 2300 | 1200 | 350 | 15850 | 24031.19 | 8181.19 | 34.04%
No project/line item can have a negative Budget remainingunless the steering committee has previously approved the over expenditure.
If % budget remaining for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.