## 2021 Budget
2020
Expense | [14 empty] | Notes
| 2021 Budget | 2021 Actual | 2020 Budget | 2020 Actual | 2019 Budget | 2019 Actual | 2018 Budget | 2018 Actual | 2017 budget | 2017 actual | 2016 Budget | 2016 Actual | 2015 Budget | 2015 Actual
Admin | 2500 |  | 3000 | 3050 | 3000 | 2660 | 3000 | 3525 | 3000 | 3335 | 2500 | 3980 | 2000 | 4111.25 |  | projected $500 less than 2020 due to gained familiarity of budget process
Boundary UWR | 500 |  | 0 | 100 | 0 | 0 | 0 | 0 | 4220 | 4220 | 2355.75 | 6299.33 | 1000 | 3780 |  | Needs a little balance for ongoing report maintenance
WK UWR | 500 |  | 0 | 500 | 3000 | 0 | 3000 | 2920 | 1780 | 0 | 0 | 0 | 0 | 0 |  | Needs a little balance for ongoing report maintenance
Biodiversity Report | 500 |  | 3000 | 2900 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Needs a little balance for ongoing report maintenance
Update resultants, depletion | 5000 |  | 8500 | 7400 | 6500 | 4740 | 7500 | 7850 | 10000 | 8000 | 2000 | 12520 | 13000 | 13556.45 |  | Less work to do this year as 2020 resultants published
Website maintenance | 2000 |  | 2000 | 1350 | 2000 | 3360 | 2750 | 2000 | 1850 | 2920 | 1850 | 1860 | 1000 | 1106.25 |  | Same anticipated cost as 2020
Subscriber support | 1500 |  | 1500 | 1200 | 2500 | 1040 | 2500 | 2320 | 1500 | 3300 | 1000 | 1320 | 0 | 0 |  | Same anticipated cost as 2020
Quality Assurance | 3000 |  | 6031.19 | 4550 | 2000 | 5720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2642.5 |  | Reduced to $3000 as QA procedures have been documented
Unallocated | 4507 |  | 0 | 0 | 6913.1 |  | 9640.65 |  | 0 | 0
Total Expenses | 20007 |  | 24031.19 | 21050 | 25913.1 | 17520 | 28390.65 | 18615 | 22350 | 21775 | 9705.75 | 25979.33 | 17000 | 25196.45
Revenue
Assuming No Change from 2018 AAC Allocations
|  | 2021 at $.005 |  | 2020 at $.005 |  | 2019 at $.005 |  | 2018 at $0.01 | 2018 Received + Committed | 2017 at $0.015
FLNRO |  | 2500 |  | 2500 |  | 2500 |  | 5000 | 4500 | 5000
BCTS |  | 3534.37 |  | 3534.37 |  | 3590.52 |  | 7181.04 | 7181.04 | 10771.56
Kalesnikoff |  | 500 |  | 500 |  | 500 |  | 899.5 | 899.5 | 1349.25
Interfor |  | 5688.61 |  | 5688.61 |  | 5688.61 |  | 11377.21 | 11377.21 | 17065.82
NACFOR |  | 500 |  | 500 |  | 500 |  | 500 | 500 | 750
Atco |  | 858.97 |  | 858.97 |  | 858.97 |  | 1717.94 | 1717.94 | 2576.91
SIFCo |  | 500 |  | 500 |  | 500 |  | 500 | 500 | 750
KDCFS |  | 500 |  | 500 |  | 500 |  | 500 | 500
Vaagen - West Boundary CF |  | 500 |  | 500 |  | 500 |  | 500 | 500
Vaagen - Osoyoos Indian Band |  | 500 |  | 500 |  | 500 |  | 500 | 500
Tolko |  | 500
Stella-Jones |  | 500
Cooper Creek Cedar |  | 500
Total Revenue |  | 17081.95 |  | 15581.95 |  | 15638.1 |  | 28675.69 | 28175.69 | 38263.54
Surplus/Deficit Carry over
Debt / Credit |  | 2925.05 |  | 8393.1 |  | 10275 |  | 214.96 |  | -15913.54
Total Balance |  | 20007 |  | 23975.05 |  | 25913.1 |  | 28890.65 |  | 22350

## Jan 2021
HLPORS Financial Report Jan 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 600 | 2500 | 1900 | 1900 | 76% |  |  | Finalizing expenditure for 2020, work on 2021 budget, resolving misunderstanding about SIFCO membership, Finance subcomitee and group meetings
Boundary UWR (Ian D) |  | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). |  | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) |  | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) |  | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) | 300 | 300 | 2000 | 1700 | 1700 | 85% |  |  | Fixing a security problem, the help pages that now include all the tables were outsdide the password protected content and thus discoverable on Googls
Subscriber support (Ian, Ian D.) | 50 | 50 | 1500 | 1450 | 1450 | 96.67% |  |  | Investigating changes in ownership noted by Gavin Fox
Quality Assurance |  | 0 | 3000 | 3000 | 3000 | 100%
Unallocated |  | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 950 | 20007 | 19057 | 19057 | 95.25%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Feb 2021
HLPORS Financial Report Feb 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 200 | 800 | 2500 | 1700 | 1700 | 68% |  |  | Preparing and sending out Subscription agreements
Boundary UWR (Ian D) |  |  | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). |  |  | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) |  |  | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) |  |  | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) | 300 |  | 300 | 2000 | 1700 | 1700 | 85%
Subscriber support (Ian, Ian D.) | 50 |  | 50 | 1500 | 1450 | 1450 | 96.67%
Quality Assurance |  |  | 0 | 3000 | 3000 | 3000 | 100%
Unallocated |  |  | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 200 | 1150 | 20007 | 18857 | 18857 | 94.25%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Mar 2021
HLPORS Financial Report Mar 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 200 | 450 | 1250 | 2500 | 1250 | 1250 | 50% |  |  | Subscription agreements for new subscribers, Meeting, finance reports, updating minutes/reports on website
Boundary UWR (Ian D) |  |  |  | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). |  |  |  | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) |  |  |  | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) |  |  |  | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) | 300 |  |  | 300 | 2000 | 1700 | 1700 | 85%
Subscriber support (Ian, Ian D.) | 50 |  | 100 | 150 | 1500 | 1350 | 1350 | 90% |  |  | Review of ski tenure classification for Randy Waterous
Quality Assurance |  |  | 250 | 250 | 3000 | 2750 | 2750 | 91.67% |  |  | Review of errors in all parks from INCOSADA classification in VRI, first raised by Kathleen McGuiness
Unallocated |  |  |  | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 200 | 800 | 1950 | 20007 | 18057 | 18057 | 90.25%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Apr 2021
HLPORS Financial Report Apr 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30th | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 200 | 450 | 250 | 1500 | 2500 | 1000 | 1000 | 40% |  |  | Subscription agreements for new Cooper Creek Cedar, 2021 Invoices, finance reports
Boundary UWR (Ian D) |  |  |  |  | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). |  |  |  |  | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) |  |  |  |  | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) |  |  |  |  | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) | 300 |  |  | 100 | 400 | 2000 | 1600 | 1600 | 80% |  |  | Fix update tool - server down
Subscriber support (Ian, Ian D.) | 50 |  | 100 | 150 | 300 | 1500 | 1200 | 1200 | 80% |  |  | Prep and meeting for new subscribers
Quality Assurance |  |  | 250 |  | 250 | 3000 | 2750 | 2750 | 91.67%
Unallocated |  |  |  |  | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 200 | 800 | 500 | 2450 | 20007 | 17557 | 17557 | 87.75%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## May 2021
HLPORS Financial Report May 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30th | May1 - May 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 200 | 450 | 250 | 150 | 1650 | 2500 | 850 | 850 | 34% |  |  | meeting, costing out potential site improvements
Boundary UWR (Ian D) | [5 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [5 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [5 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [5 empty] | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) | 300 |  |  | 100 | 100 | 500 | 2000 | 1500 | 1500 | 75%
Subscriber support (Ian, Ian D.) | 50 |  | 100 | 150 |  | 300 | 1500 | 1200 | 1200 | 80% |  |  | Update website with minutes and financial report
Quality Assurance |  |  | 250 |  |  | 250 | 3000 | 2750 | 2750 | 91.67%
Unallocated | [5 empty] | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 200 | 800 | 500 | 250 | 2700 | 20007 | 17307 | 17307 | 86.5%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## June 2021
HLPORS Financial Report June 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30th | May1 - May 31 | June 1 - June 30 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 200 | 450 | 250 | 150 | 200 | 1850 | 2500 | 650 | 650 | 26% |  |  | Prep budgets, user meeting and call for new users
Boundary UWR (Ian D) | [6 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [6 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [6 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [6 empty] | 0 | 5000 | 5000 | 5000 | 100%
Website maintenance (Ian, Ian D.) | 300 |  |  | 100 | 100 |  | 500 | 2000 | 1500 | 1500 | 75%
Subscriber support (Ian, Ian D.) | 50 |  | 100 | 150 |  |  | 300 | 1500 | 1200 | 1200 | 80%
Quality Assurance |  |  | 250 |  |  |  | 250 | 3000 | 2750 | 2750 | 91.67%
Unallocated | [6 empty] | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 200 | 800 | 500 | 250 | 0 | 2900 | 20007 | 17107 | 17107 | 85.51%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## July 2021
HLPORS Financial Report July 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30th | May1 - May 31 | June 1 - June 30 | July 1 - July 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 200 | 450 | 250 | 150 | 200 |  | 1850 | 2500 | 650 | 650 | 26%
Boundary UWR (Ian D) | [7 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [7 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [7 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [6 empty] | 2100 | 2100 | 5000 | 2900 | 2900 | 58% |  | Started work on Depletion
Website maintenance (Ian, Ian D.) | 300 |  |  | 100 | 100 |  |  | 500 | 2000 | 1500 | 1500 | 75%
Subscriber support (Ian, Ian D.) | 50 |  | 100 | 150 |  |  |  | 300 | 1500 | 1200 | 1200 | 80%
Quality Assurance |  |  | 250 |  |  |  |  | 250 | 3000 | 2750 | 2750 | 91.67%
Unallocated | [7 empty] | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 200 | 800 | 500 | 250 | 200 | 2100 | 5000 | 20007 | 15007 | 15007 | 75.01%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Aug 2021
HLPORS Financial Report Aug 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30th | May1 - May 31 | June 1 - June 30 | July 1 - July 31 | Aug 1 Aug 31 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 200 | 450 | 250 | 150 | 200 |  |  | 1850 | 2500 | 650 | 650 | 26%
Boundary UWR (Ian D) | [8 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [8 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [8 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [6 empty] | 2100 | 2800 | 4900 | 5000 | 100 | 100 | 2% |  | Built resultant
Website maintenance (Ian, Ian D.) | 300 |  |  | 100 | 100 |  |  |  | 500 | 2000 | 1500 | 1500 | 75%
Subscriber support (Ian, Ian D.) | 50 |  | 100 | 150 |  |  |  |  | 300 | 1500 | 1200 | 1200 | 80%
Quality Assurance |  |  | 250 |  |  |  |  | 2800 | 3050 | 3000 | -50 | -50 | -1.667% |  | QA completed on resultant and depletion
Unallocated | [8 empty] | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 200 | 800 | 500 | 250 | 200 | 2100 | 5600 | 10600 | 20007 | 9407 | 9407 | 47.02%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.

## Sep 2021
HLPORS Financial Report Sep 2021
Income
2020 Credit Carry Over | 2925.05
2021 Contribution | 17081.95
Total Available Funds | 20007
Expenses
| Jan 1 - Jan 31 | Feb 1 - Feb 28 | Mar 1 - Mar 31 | Apr 1 - Apr 30th | May1 - May 31 | June 1 - June 30 | July 1 - July 31 | Aug 1 - Aug 31 | Sep1 - Sep 30 | YTD | Annual Allocation | Budget Remaining | Cost Variance | % Cost Varianc | % Complete | Forecast at Completion | Notes
Admin(Ian, Ian D) | 600 | 200 | 450 | 250 | 150 | 200 |  |  | 100 | 1950 | 2500 | 550 | 550 | 22% |  | budget reports, and updating reports/minutes on website
Boundary UWR (Ian D) | [9 empty] | 0 | 500 | 500 | 500 | 100%
WK UWR (Ian D). | [9 empty] | 0 | 500 | 500 | 500 | 100%
Biodiversity Report (Ian D) | [9 empty] | 0 | 500 | 500 | 500 | 100%
Update resultants, depletion (Ian D.) | [6 empty] | 2100 | 2800 |  | 4900 | 5000 | 100 | 100 | 2%
Website maintenance (Ian, Ian D.) | 300 |  |  | 100 | 100 |  |  |  |  | 500 | 2000 | 1500 | 1500 | 75%
Subscriber support (Ian, Ian D.) | 50 |  | 100 | 150 |  |  |  |  | 300 | 600 | 1500 | 900 | 900 | 60% |  | chasing bug in the update tool reported by Tom Haukass
Quality Assurance |  |  | 250 |  |  |  |  | 2800 |  | 3050 | 3000 | -50 | -50 | -1.667%
Unallocated | [9 empty] | 0 | 4507 | 4507 | 4507 | 100%
Total Expenses | 950 | 200 | 800 | 500 | 250 | 200 | 2100 | 5600 | 400 | 11000 | 20007 | 9007 | 9007 | 45.02%
· Cost Variance (CV) = Annual Allocation (AA) – Year To Date expenditure (YTD)
· Percent Cost Variance (CV%) = Cost Variance (CV) / Annual Allowance (AA)
· Positive CV and CV% indicates the project/line item is under budget
· Negative CV and CV% indicates the project/line item is over budget
No project/line item can have a negative Cost Variance (CV) unless the steering committee has previously approved the over expenditure.
If cost variance for a line item is less than 15%, options will be developed along with a rationale for review and approval by the steering committee.